## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-07 | 7 | Jane Doe | Completed
Market Analysis | 2024-03-08 | 2024-03-25 | 18 | John Smith | In Progress
Product Development | 2024-03-26 | 2024-05-15 | 51 | Alex Turner | Planned
Pilot Testing | 2024-05-16 | 2024-06-10 | 35 | Sarah Lee | Not Started
Full Launch | 2024-06-11 | 2024-07-31 | 51 | Team Leadership | Planned