## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Business Strategy Review | 2024-03-01 | 2024-03-15 | 15 days | Operations Director | In Progress
Budget Allocation Planning | 2024-03-16 | 2024-04-05 | 21 days | Finance Manager | Not Started
Procurement Process Optimization | 2024-04-06 | 2024-05-10 | 45 days | Procurement Lead | Planned
Inventory & Supply Chain Review | 2024-05-11 | 2024-06-15 | 45 days | Supply Chain Analyst | Not Started
Operational KPIs Setup | 2024-06-16 | 2024-07-31 | 46 days | Operations Analyst | Scheduled