## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research | 2024-03-01 | 2024-03-15 | 15 | Marketing Team | On Track
Product Development | 2024-03-16 | 2024-05-31 | 76 | Engineering Team | In Progress
Quality Assurance Testing | 2024-06-01 | 2024-06-30 | 30 | QA Department | Not Started
Launch Planning | 2024-07-01 | 2024-07-15 | 15 | Operations Manager | Planned
Go-Live Execution | 2024-07-16 | 2024-07-31 | 16 | Operations Team | Pending Approval