## Business Operations Gantt Chart
Task Name | Start Date | End Date | Duration (Days) | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | In Progress
Market Analysis & Planning | 2024-01-16 | 2024-02-05 | 21 | Completed
Resource Allocation & Hiring | 2024-02-06 | 2024-03-15 | 41 | Planned
Process Workflow Design | 2024-03-162024-04-15 | 31 | In Progress
System Integration & Testing | 2024-04-162024-06-30 | 76 | Not Started
Operational Training & Rollout | 2024-07-012024-08-15 | 56 | Planned
Performance Review & Optimization | 2024-08-162024-10-31 | 77 | Not Started