## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | Marketing Team | On Track
Product Requirements Finalization | 2024-03-16 | 2024-04-05 | 21 | Product Manager | In Progress
Development Planning & Scheduling | 2024-04-06 | 2024-05-10 | 35 | Engineering Team | Not Started
Quality Assurance & Testing | 2024-05-11 | 2024-06-15 | 35 | QA Team | Not Started
Deployment & Launch Preparation | 2024-06-16 | 2024-07-05 | 21 | Operations Team | Not Started
Post-Launch Review & Feedback Collection | 2024-07-06 | 2024-07-31 | 26 | Customer Success Team | Not Started