## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Jane Doe
Market Research | 2024-03-06 | 2024-03-15 | 10 | John Smith
Product Design | 2024-03-16 | 2024-04-10 | 25 | Alex Johnson
Development Phase | 2024-04-11 | 2024-06-30 | 81 | Team B
Testing & Quality Assurance | 2024-07-01 | 2024-07-15 | 15 | Sarah Lee
Launch Preparation | 2024-07-16 | 2024-07-31 | 16 | Mark Brown
Product Launch | 2024-08-01 | 2024-08-05 | 5 | All Teams