## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Business Plan Finalization | 2024-03-15 | 2024-03-25 | 11 | Jane Smith | On Track
Market Research & Analysis | 2024-03-26 | 2024-04-10 | 15 | Mike Johnson | In Progress
Product Development Start | 2024-04-11 | 2024-05-05 | 25 | Sarah Lee | Not Started
Pilot Testing Launch | 2024-05-06 | 2024-05-18 | 13 | David Brown | Planned
Final Product Review & Approval | 2024-05-19 | 2024-05-31 | 13 | Jane Smith | On Track