## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 days | Marketing Team | On Track
Product Roadmap Finalization | 2024-03-16 | 2024-04-05 | 21 days | Product Manager | In Progress
Team Onboarding & Training | 2024-04-06 | 2024-04-18 | 13 days | HR & Ops Lead | Scheduled
Launch Planning Workshop | 2024-04-19 | 2024-05-03 | 16 days | Operations Director | Not Started
Initial Sales & Distribution Setup | 2024-05-04 | 2024-05-31 | 28 days | Sales & Logistics | Planned