## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | Marketing Team | In Progress
Product Development Planning | 2024-03-16 | 2024-04-10 | 35 | Product Team | Not Started
Budget Allocation Review | 2024-04-11 | 2024-04-18 | 8 | Finance Team | Planned
Team Training & Onboarding | 2024-04-19 | 2024-05-03 | 15 | HR & Operations Team | Scheduled
Process Optimization Workshop | 2024-05-04 | 2024-05-11 | 8 | Operations Team | Not Started
Final Review & Launch Planning | 2024-05-12 | 2024-05-31 | 20 | All Teams | In Planning