## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Smith | Completed
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 | Sarah Lee | In Progress
Business Process Mapping | 2024-04-11 | 2024-05-05 | 35 | Mike Chen | Not Started
Operational Planning & Budgeting | 2024-05-06 | 2024-05-31 | 26 | Lisa Wong | Planned
Resource Allocation & Training | 2024-06-01 | 2024-07-15 | 65 | David Kim | Not Started
Performance Review & Optimization | 2024-07-16 | 2024-08-31 | 56 | Emma Ross | Scheduled