## Worksheet
Task/Activity | Start Date | End Date | Status | Responsible | Progress (%)
Business Plan Finalization | 2024-01-15 | 2024-01-30 | In Progress | Manager A | 75%
Market Research & Analysis | 2024-02-01 | 2024-02-15 | On Track | Analyst B | 100%
Milestone: Strategy Approval | 2024-02-16 | 2024-02-16 | Completed | Director C | 100%
Resource Allocation & Budgeting | 2024-03-01 | 2024-03-15 | Pending Review | Finance Team | 30%
Operations Process Redesign | 2024-03-16 | 2024-04-30 | Not Started | Operations Lead D | 0%
Milestone: Pilot Launch | 2024-05-01 | 2024-05-01 | Planned | Project Manager E | 0%
Performance Monitoring & Review | 2024-05-02 | 2024-06-30 | Not Started | Reporting Team F | 0%