## Worksheet
Date | Task | Owner | Priority | Status | Deadline | Resources Required | Notes/Remarks
01/04/2024 | Finalize Q1 Budget Proposal | John Smith | High | Pending | 05/04/2024 | Finance Team, Excel, Presentation Tools | Include departmental cost analysis and ROI projections.
03/04/2024 | Conduct Stakeholder Meeting | Emily Chen | Moderate | <>Completed03/04/2024 | Marketing Team, External Clients, Meeting Room | Agenda distributed 3 days prior. Attendance: 15.
05/04/2024 | Review Supply Chain Risk Report | Michael Lee | High | In Progress | 07/04/2024 | Sales, Logistics, Data Analysts | Identify vulnerabilities in regional suppliers.
07/04/2024 | Update Operations KPI Dashboard | Sarah Johnson | Moderate | Completed | 07/04/2024 | Data Team, BI Tools (Power BI) | Added new KPIs for on-time delivery and error rates.
09/04/2024 | Organize Internal Training Session | David Kim | Low | Scheduled | 10/04/2024 | HR Team, 3 trainers, Learning Platform | Focused on new ERP system usage.
12/04/2024 | Prepare Quarterly Business Review (QBR) | Team Lead | High | In Progress | 15/04/2024 | Operations, Finance, Marketing Heads | Include performance metrics and action plans.