## Worksheet
Task ID | Project Name | Objective | Responsible Party | Start Date | End Date | Status | Budget (USD) | Milestone | Dependencies
P-OP-001 | Process Optimization Initiative | Streamline operational workflows to reduce processing time by 20% | Operations Manager | 2024-03-15 | 2024-06-30 | On Track | $150,000 | Phase 1 Complete | HR Process Review, IT System Upgrade
P-OP-002 | Supply Chain Enhancement | Reduce lead times by 15% through vendor renegotiation and logistics review | Logistics Director | 2024-04-01 | 2024-07-15 | In Progress | $200,000 | Vendor Assessment Complete | Finance Approval Pending
P-OP-003 | Budget Reallocation Review | Reassess operational budgets to align with quarterly revenue goals | Finance Lead | 2024-03-20 | 2024-05-31 | Completed | $75,000 | Final Approval Received | None
P-OP-004 | Customer Feedback Integration | Implement customer insights into daily operations to improve service delivery | Customer Experience Officer | 2024-05-01 | 2024-08-31 | Planned | $90,000 | Data Collection Phase | Process Optimization Initiative (P-OP-001)