## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Dependencies | Resources Required | Budget (USD)
P-001 | Market Research & Analysis | Jane Smith | 2024-03-15 | 2024-04-15 | In Progress | High | P-003, P-004 | Marketing Team, Data Analysts | $15,000
P-002 | Product Roadmap Finalization | Michael Lee | 2024-03-18 | 2024-05-30 | Pending Approval | Moderate | P-001, P-005 | Product Managers, UX Designers | $25,000
P-003 | Customer Feedback Collection | Sarah Kim | 2024-03-20 | 2024-04-10 | Completed | High | P-001 | Campaign Team, Support Staff | $8,500
P-004 | Competitor Benchmarking Report | David Brown | 2024-03-25 | 2024-04-15 | In Progress | Moderate | P-001 | Research Analysts, Strategy Team | $12,000
P-005 | Go-to-Market Strategy Design | Emma Taylor | 2024-04-10 | 2024-06-15 | Pending Approval | High | P-002, P-006 | Sales Team, Marketing Team | $35,000
Project Plan - Analysis View ¦ Purpose: Business Operations ¦ Template Type: Project Plan ¦ Style/Version: Analysis View