## Worksheet
Project ID | Project Name | Purpose | Initiator | Start Date | End Date | Budget (USD) | Status | Responsibility Team | Milestones | Key Deliverables | Risks | Dependencies | Approved By
OP-2024-001 | Digital Transformation of Finance Operations | Business Operations | Jane Doe | 2024-03-15 | 2025-06-30 | $1,250,000 | On Track | Finance & IT Leadership Team | Phase 1: System Audit (Mar 2024) Phase 2: Process Redesign (May 2024) Phase 3: Go-Live (June 2025) | Integrated Financial Reporting Platform Automated Expense Management System | Data migration delays Staff resistance to change | ERP integration approval Training schedule alignment | Robert Chen, CFO
OP-2024-002 | Supply Chain Optimization Initiative | Business Operations | Michael Park | 2024-04-01 | 2025-11-30 | $875,000 | In Progress | Operations & Procurement Team | Vendor Assessment (Apr 2024) Supply Chain Mapping (Jul 2024) Process Improvement Rollout (Nov 2025) | Real-time inventory dashboard Supplier performance KPIs | Vendor contract renegotiation delays Geopolitical risks | Procurement policy updates Global logistics coordination | Sarah Kim, COO
OP-2024-003 | Customer Service Efficiency Program | Business Operations | Linda Torres | 2024-05-10 | 2025-09-30 | $650,000 | Planning Phase | Customer Experience & HR Team | Needs Assessment (May 2024) Process Workflow Analysis (Jul 2024) Tool Deployment (Sep 2025) | AI-powered support chatbot Service response time improvement | Technology integration issues Lack of frontline staff buy-in | Training resource allocation Feedback loop implementation | David Liu, Customer VP