## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources Required | Notes
Define Business Operations Strategy | John Smith | 2024-03-15 | 2024-04-10 | In Progress | High | Operations Team, Strategy Lead | Align with market trends and KPIs.
Process Mapping of Core Operations | Sarah Lee | 2024-03-20 | 2024-04-15 | Pending Start | Moderate | Process Analysts, IT Support | Document current workflows and identify bottlenecks.
Implement Quality Control Procedures | Mike Chen | 2024-04-01 | 2024-05-15 | Not Started | High | Quality Team, Engineering | Introduce standardized checklists and audits.
Vendor Performance Review & Onboarding | Dana Rodriguez2024-03-25 | 2024-05-30 | Pending Start | Moderate | Purchasing, Legal, Operations | Evaluate and onboard new suppliers.
Monthly Operational Review Meetings | Operations Manager | 2024-03-15 | 2024-12-31 | Ongoing | Low | All Department Heads | Hold bi-weekly meetings to assess performance.