## Worksheet
Task | Owner | Start Date | End Date | Status | Resource Required | Dependencies | Risk Level | Budget (USD)
Market Research & Analysis | Sarah Johnson | 2024-03-15 | 2024-04-10 | In Progress | Marketing Team, Analysts | None | Low | $15,000
Product Development Planning | Michael Chen | <2024-04-11 | 2024-05-30 | Not Started | Engineering, Design Team | Market Research Complete | Medium | $120,000
Pilot Launch (Q2) | Emma Rodriguez | 2024-06-01 | 2024-06-30 | Planned | Operations, Sales, Logistics | Product Development Ready | Medium-High | $75,000
Full Scale Rollout (Q3) | David Kim | 2024-07-01 | 2024-09-30 | Not Started | All Departments, Support Teams | Pilot Launch Successful | High | $300,000
Performance Review & Optimization | Lisa Wong | 2024-10-01 | 2024-10-31 | Not Started | Analytics, Operations Team | Full Rollout Completed | Low-Medium | $25,000