## Worksheet
Project Name | Objective | Budget (USD) | Start Date | End Date | Responsible Team | Status | Key Milestones | Cost Variance | ROI Projection (%)
Supply Chain Optimization | Reduce procurement lead times by 30% | $1,200,000 | 2024-03-15 | 2024-09-30 | Logistics & Procurement Team | On Track | Vendor Onboarding (Q2), Process Automation (Q3) | -$15,000 | 18.5%
Digital Transformation Initiative | Implement ERP system to streamline operations | $2,500,000 | 2024-04-10 | 2025-12-31 | IT & Operations Leadership | In Progress | Phase 1 Deployment (Q3), Training Rollout (Q4) | +$40,000 | 25.2%
Customer Service Enhancement | Improve response time from 48h to 12h | $600,000 | 2024-05-01 | 2024-11-30 | Customer Experience Team | Completed | Training (Q2), System Integration (Q3) | -$5,000 | 12.8%