## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources
Market Research & Analysis | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | High | Marketing Team, Analysts
Product Development Planning | John Smith | <2024-03-16 | 2024-04-10 | High | Medium | Product Team, Engineers
Budget Forecasting & Financial Review | Lisa Chen | 2024-03-05 | 2024-03-25 | Completed | High | Finance Department, CFO
Operational Workflow Design | Mark Turner | 2024-04-11 | 2024-05-05 | Not Started | Medium | Operations Team, Process Analysts
Vendor Onboarding & Contracts | Sarah Lee | 2024-03-26 | 2024-04-15 | In Progress | Medium | Procurement Team, Legal