## Worksheet
Task | Owner | Start Date | End Date | Status | Resources Required | Dependencies
Market Research & Analysis | Sarah Thompson | 2024-03-15 | 2024-04-05 | In Progress | Marketing Team, Data Analysts | None
Product Development Planning | James Reed | 2024-04-06 | 2024-05-15 | Not Started | Engineering Team, UX Designers | Market Research Completed
Budget Finalization & Approval | Lisa Chen | 2024-05-16 | 2024-05-31 | Pending | Finance Department, CFO | Product Development Planning Complete
Pilot Program Launch | Michael Brooks | 2024-06-01 | 2024-07-31 | Not Started | Operations Team, Sales Team | Budget Approved
Performance Review & Optimization | Sarah Thompson | 2024-08-01 | 2024-08-31 | Not Started | Analytics Team, Operations Manager | Pilot Program Completed