## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Resources Required | Notes
Project Initiation & Planning | John Smith | 2024-03-01 | 2024-03-15 | In Progress | N/A | Project Manager, Stakeholder Team | Define objectives, scope, and key stakeholders.
Market Research & Analysis | Sarah Johnson | 2024-03-16 | 2024-04-05 | Depends on Initiation | Project Initiation & Planning | Research Analyst, Data Team | Gather competitive insights and customer trends.
Product Design & Prototyping | Michael Chen | 2024-04-06 | 2024-05-10 | Pending Approval | Market Research & Analysis | Design Team, UX Experts | Create wireframes and functional prototypes.
Development & Testing Phase | Amy Rodriguez | 2024-05-11 | 2024-07-15 | Not Started | Product Design & Prototyping | Development Team, QA Engineers | Build and test software functionality.
Pilot Launch & Feedback Collection | David Kim | 2024-07-16 | 2024-08-10 | Planned | Development & Testing Phase | MKT Team, Customer Support | Launch in a controlled environment and collect user feedback.
Full-Scale Deployment | John Smith | 2024-08-11 | 2024-09-30 | Not Started | Pilot Launch & Feedback Collection | All Teams, Operations Department | Roll out to all customers with monitoring and support.