## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources
Market Research & Analysis | Sarah Chen | 2024-03-01 | 2024-03-15 | In Progress | High | Marketing Team, Analysts
Product MVP Development | David Kim | 2024-03-16 | 2024-04-30 | On Track | High | Engineering Team, UX Designers
User Feedback Collection | Lena Torres | 2024-04-01 | 2024-05-15 | Not Started | Medium | Customer Support, QA Team
Sales Strategy Planning | James Reed | 2024-03-20 | 2024-04-15 | In Progress | High | Sales Team, Finance
Budget Forecasting & Allocation | Anna Patel | 2024-03-10 | 2024-03-31 | Completed | High | Finance Department