## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
Market Research & Analysis | Sarah Johnson | 2024-03-15 | 2024-04-01 | In Progress | High |  | Collect consumer trends and competitive data.
Product Development Roadmap | David Chen | 2024-03-20 | 2024-05-15 | Planned | High | Market Research & Analysis | Finalize features based on research findings.
Budget Planning & Allocation | Lisa Park | 2024-03-18 | 2024-04-10 | On Track | Medium |  | Prepare operational and marketing budgets.
Team Training & Onboarding | Michael Reed | 2024-04-01 | 2024-04-15 | Scheduled | Medium | Product Development Roadmap | New hires to complete onboarding modules.
Process Optimization Review | Elena Torres | 2024-04-10 | 2024-05-05 | Not Started | High | Budget Planning & Allocation | Assess current workflows for efficiency gains.