## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Market Research & Analysis | Emma Johnson | 2024-03-15 | 2024-03-30 | In Progress | 65% | None | Preliminary data gathered; awaiting client review.
Product Requirements Specification | David Chen | 2024-03-20 | 2024-04-10 | Pending Approval | 30% | Market Research Complete | Final version to be approved by stakeholders.
Development Phase - MVP Build | Sarah Lee | 2024-04-15 | 2024-05-15 | Not Started | - | Requirements Approved | Frontend and backend architecture in design phase.
User Testing & Feedback Collection | James Wilson | 2024-05-20 | 2024-06-10 | Planned | - | MVP Build Complete | Target audience feedback to be analyzed and reported.
Post-Launch Support & Optimization | Lisa Park | 2024-06-15 | 2024-09-30 | Not Started | - | User Testing Complete | Monitoring performance and resolving bugs post-launch.