## Worksheet
Date | Project Name | Team Member | Task Description | Status | Time Spent (hrs) | Next Steps
2023-10-05 | Website Redesign Launch | Jane Smith | Finalize UI/UX mockups and conduct stakeholder review | In Progress | 8.5 | Present mockups to executives by EOD tomorrow
2023-10-05 | Supply Chain Audit | Mike Johnson | Review delivery timelines and identify bottlenecks | Pending Approval | 4 | Share findings with Operations Manager by end of week
2023-10-05 | Customer Onboarding Process | Sarah Lee | Update SOPs for new customer intake workflow | Completed | 2.5 | Train team on updated process next week
2023-10-06 | Marketing Campaign Review | David Kim | Analyze performance data from Q3 campaign | Not Started | - | Prepare report for strategy meeting on 10-10