## Worksheet
Project ID | Project Name | Start Date | End Date | Status | Owner | Budget (USD) | Progress (%) | Next Milestone | Risk Level
PROJ-001 | Sales Process Automation | 2024-03-15 | 2024-07-30 | On Track | Sarah Chen | $150,000 | 75% | Implement CRM Integration | Medium
PROJ-002 | <Supply Chain Optimization | 2024-04-01 | 2024-11-30 | In Progress | Michael Torres | $300,000 | 45% | Finalize Vendor Contracts | High
PROJ-003 | Office Space Reconfiguration | 2024-05-10 | 2024-09-15 | Planned | Lisa Wang | $75,000 | 10% | Secure Interior Design Approval | Low
PROJ-004 | Customer Feedback System Launch | 2024-06-01 | 2024-12-31 | Pending Approval | David Kim | $100,000 | 25% | Submit to CTO for Review | Medium