## Worksheet
Week | Project Name | Owner | Status | Key Activities | Deliverables | Risks & Issues | Next Steps
Week 1 | Onboarding Process Optimization | Sarah Johnson | In Progress | User feedback collection, process mapping | Process flow diagram, revised onboarding checklist | Lack of IT access for testing | Coordinate with IT to schedule access
Week 2 | Supplier Contract Review | Michael Reed | Planned | Review existing contracts, identify renewal dates | Updated supplier agreement summary | Potential price increase by 15% | Negotiate revised terms with suppliers
Week 3 | Team Capacity Assessment | Lisa Chen | Completed | Workload analysis, skill gap evaluation | Team capacity report, training recommendations | None reported | Share findings with management
Week 4 | Budget Reallocation Proposal | David Kim | Drafting | Analyze current spending, identify areas for cut/savings | Proposed budget reallocation plan | Uncertainty in revenue forecast | Refine proposal based on updated forecasts