## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Milestones | Budget (USD) | Priority
Market Research & Analysis | Sarah Johnson | 2024-03-15 | 2024-04-10 | In Progress | None | Initial Data Collection | 15,000 | High
Product Development Phase 1 | Michael Chen | 2024-04-11 | 2024-06-30 | Not Started | Market Research Complete | Prototype Review | 75,000 | Critical
Regulatory Compliance Review | Lisa Torres | 2024-05-01 | 2024-05-31 | Planned | Product Development Phase 1 Complete | Approval Received | 20,000 | High
Pilot Launch in Target Market | David Kim | 2024-07-01 | 2024-08-31 | Not Started | Regulatory Approval Received | Pilot Success Metrics | 50,000 | High
Full Market Rollout Strategy | Elena Rodriguez | 2024-09-01 | 2024-11-30 | Not Started | Pilot Launch Successful | National Campaign Start | 120,000 | Critical