## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Notes
Project Initiation | John Smith | 2024-01-15 | 2024-01-25 | Completed | - | Finalized business objectives and scope.
Stakeholder Workshops | Sarah Johnson | 2024-01-26 | 2024-01-31 | In Progress | Project Initiation | Gathered requirements from key departments.
Feasibility Study | Mike Brown | 2024-02-01 | 2024-02-15 | Planned | Stakeholder Workshops | Assess technical, financial, and operational feasibility.
Process Mapping | Lisa Chen | 2024-02-16 | 2024-03-01 | Not Started | Feasibility Study | Document current operational workflows.
Resource Allocation | David Lee | 2024-03-02 | 2024-03-15 | Planned | Process Mapping | Assign roles, budget, and team members.
Risk Assessment | Emma Wilson | 2024-03-16 | 2024-03-31 | In Progress | Resource Allocation | Identify and mitigate operational risks.