## Worksheet
Project Name | Start Date | End Date | Status | Owner | Next Milestone | Progress (%)
Onboarding Process Optimization | 2024-03-01 | 2024-05-31 | In Progress | Jane Smith | Finalize Training Modules (Apr 15) | 65%
Supplier Risk Assessment | 2024-04-01 | 2024-06-30 | Pending Approval | Michael Chen | Complete Vendor Audit (May 18) | 30%
Office Space Utilization Review | <2024-03-15 | 2024-07-31 | Planned | Sarah Lee | Initial Space Analysis (Apr 30) | 0%
Procurement Policy Update | 2024-05-01 | 2024-08-31 | Not Started | David Kim | Pilot Phase Begins (May 15) | 0%