## Worksheet
Task | Owner | Start Date | End Date | Status | Milestone? | Dependencies | Resources Required | Risk Level | Notes
Market Research & Analysis | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | Yes |  | Research Team, Data Analysts | Medium | Gather customer insights and competitor benchmarks.
Product Development Planning | John Smith | 2024-03-16 | 2024-04-10 | Planned | Yes | Market Research & Analysis | Product Manager, Engineering Lead | Low | Finalize product specifications and timeline.
Prototype Development | Alex Johnson | 2024-04-11 | 2024-05-15 | Not Started | Yes | Product Development Planning | Design Team, Engineers | Medium | Build a functional prototype for user testing.
User Testing & Feedback Loop | Sarah Lee | 2024-05-16 | 2024-06-10 | Not Started | Yes | Prototype Development | UX Researchers, Test Subjects | Medium | Collect user feedback and refine product.
Final Product Review & Approval | Michael Brown | 2024-06-11 | 2024-06-25 | Planned | Yes | User Testing & Feedback Loop | Product Manager, CFO, Legal | High | Final validation of product before launch.
Go-Live & Launch Preparation | Emma Davis | 2024-06-26 | 2024-07-10 | Not Started | Yes | Final Product Review & Approval | Marketing, Operations, IT | Low | Coordinate launch events and training.