## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Status | Progress (%)
Market Analysis & Feasibility Study | 2024-03-15 | 2024-04-10 | Marketing Team | 15,000.00 | On Track | 95%
Procurement of Equipment & Supplies | 2024-04-11 | 2024-05-15 | Procurement Department | 75,000.00 | In Progress | 65%
Financial Modeling & Forecasting | 2024-05-16 | 2024-06-30 | Finance Division | 45,000.00 | Not Started | 0%
Operational Setup & Staff Onboarding | 2024-07-01 | 2024-08-15 | HR & Operations Team | 60,000.00 | Not Started | 0%
Performance Review & Adjustment Phase | 2024-08-16 | 2024-09-30 | Executive Management | 35,000.00 | Not Started | 0%