## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Priority
Project Initiation & Planning | 2024-03-15 | 2024-03-25 | Project Manager | In Progress | High
Market Research & Analysis | 2024-03-26 | 2024-04-05 | Marketing Analyst | Not Started | High
Business Model Finalization | 2024-04-06 | 2024-04-15 | CEO & CFO | Not Started | High
Budget Planning & Allocation | 2024-04-16 | 2024-04-25 | Finance Team | Not Started | Medium
Team Recruitment & Onboarding | 2024-04-26 | 2024-05-10 | HR Manager | Not Started | Medium
Operational Workflow Design | 2024-05-11 | 2024-05-30 | Operations Lead | Not Started | Medium
Review & Approval Process | 2024-06-01 | 2024-06-15 | Board of Directors | Not Started | High