## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Notes
Project Initiation & Planning | 01/15/2024 | 01/30/2024 | Operations Manager | Completed | Finalized project scope and objectives.
Resource Allocation | 02/01/2024 | 02/14/2024 | HR & Finance Team | In Progress | Team assignments confirmed.
Process Mapping & Workflow Design | 02/15/2024 | 03/15/2024 | Operations Analysts | Not Started | Draft workflows under review.
Training & Onboarding | 03/20/2024 | 04/10/2024 | Training Coordinator | Planned | Schedule finalized with staff.
Performance Review & Adjustment | 04/15/2024 | 04/30/2024 | Operations Manager | Not Started | KPIs to be evaluated post-execution.