## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Milestones
Market Research & Analysis | Sarah Chen | 2024-03-01 | 2024-03-15 | In Progress | Initial Strategy Draft | Completion of Competitor Report
Business Model Development | James Reed | 2024-03-16 | 2024-04-05 | Not Started | Market Research Report | Model Validation Review
Financial Planning & Budgeting | Lisa Park | 2024-04-06 | 2024-04-18 | Planned | Business Model Finalized | Budget Approval Sign-off
Legal & Compliance Review | David Kim | 2024-04-19 | 2024-05-03 | Not Started | Financial Plan Submitted | Regulatory Clearance Obtained
Operations Setup & Staffing | Maria Gomez | 2024-05-04 | 2024-06-15 | Not Started | Legal Compliance Approved | First Operations Kickoff
System Integration & Technology Deployment | Thomas Wu | 2024-06-16 | 2024-07-30 | Planned | Operations Setup Complete | System Go-Live
Performance Monitoring & Optimization | Elena Martinez | 2024-08-01 | Ongoing | Not Started | System Go-Live Completed | Monthly KPI Review