## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Notes
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Alex Johnson | Completed | Finalized project scope and objectives.
Market Research & Analysis | 2024-03-16 | 2024-04-05 | Sarah Lee | In Progress | Gathering customer feedback and competitive insights.
Product Design & Prototyping | 2024-04-06 | 2024-05-10 | Mike Chen | Not Started | Drafting initial design concepts and creating prototypes.
Development & Testing | 2024-05-11 | 2024-07-30 | David Patel | Planned | Software development and quality assurance cycles.
Launch & Marketing Campaign | 2024-08-01 | 2024-08-31 | Lisa Wong | Not Started | Coordinate digital and traditional marketing efforts.
Post-Launch Review & Feedback | 2024-09-01 | 2024-09-30 | Team Lead | Not Started | Evaluate performance and user feedback for future improvements.