## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-15 | Operations Director | Completed | 100%
Market Analysis & Planning | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | 75%
Resource Allocation | 2024-04-11 | 2024-04-25 | HR & Finance Team | Planned | 0%
Process Redesign Workshop | 2024-04-26 | 2024-05-10 | Operations Managers | Pending | 0%
Implementation Phase Start | 2024-05-11 | 2024-07-31 | Project Lead Team | Not Started | 0%
Performance Review & Adjustment | 2024-08-01 | 2024-08-15 | Operations Director | Planned | 0%