## Worksheet
Task | Responsible Party | Start Date | End Date | Status | Priority
Market Research & Analysis | Marketing Team | 2024-03-01 | 2024-03-15 | In Progress | High
Process Workflow Design | Operations Department | 2024-03-16 | 2024-04-05 | Planned | High
Budget Allocation Finalization | Finance Team | 2024-04-06 | 2024-04-10 | Not Started | Medium
Vendor Onboarding & Contracting | Procurement Team | 2024-04-11 | 2024-05-03 | Scheduled | High
Staff Training & Onboarding | HR & Operations | 2024-05-04 | 2024-05-31 | Not Started | Medium
Performance Review & Adjustment | Operations Manager | 2024-06-01 | 2024-06-30 | Planned | Low