## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Progress (%)
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Operations Manager | Completed | 100%
Resource Allocation & Team Setup | 2024-03-16 | 2024-04-05 | HR & Operations Team | In Progress | 75%
Process Documentation & Workflow Design | 2024-04-06 | 2024-05-10 | Process Analysts | Not Started | 0%
System Integration & Tech Setup | 2024-05-11 | 2024-06-30 | IT & Operations Lead | Planned | 0%
Performance Monitoring & KPI Review | 2024-07-01 | 2024-09-30 | Business Analytics Team | Not Started | 0%
Final Review & Operational Rollout | 2024-10-01 | 2024-10-31 | CEO & Operations Director | Not Started | 0%