## Worksheet
Task | Start Date | End Date | Responsible Person | Status
Project Initiation | 2024-01-15 | 2024-01-20 | John Smith | Completed
Market Research | 2024-01-21 | 2024-02-05 | Lisa Chen | In Progress
Business Model Development | 2024-02-06 | 2024-03-15 | Mike Rodriguez | Planned
Budget Finalization | 2024-03-16 | 2024-03-25 | Sarah Kim | Not Started
Stakeholder Review Meeting | 2024-03-26 | 2024-03-28 | David Lee | Scheduled