## Worksheet
Task | Start Date | End Date | Responsible Party | Status
Market Research | 2024-03-01 | 2024-03-15 | Marketing Team | In Progress
Business Plan Finalization | 2024-03-16 | 2024-03-31 | CEO | Not Started
Vendor Onboarding | 2024-04-01 | 2024-04-10 | Operations Manager | Planned
Office Setup & Equipment | 2024-04-11 | 2024-04-25 | Admin Staff | Not Started
Staff Training & Onboarding | 2024-05-01 | 2024-05-15 | HR Director | Planned
First Product Launch (Pilot) | 2024-06-01 | 2024-06-30 | Product Manager | Scheduled