## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Status | Next Milestone
Project Initiation | 01/03/2024 | 05/03/2024 | Strategy & Planning Team | Feasibility report, Stakeholder analysis | Completed | Approval of project charter
Requirements Gathering | 06/03/2024 | 15/04/2024 | Business Analysis Team | Functional & non-functional requirements document | In Progress | Requirement sign-off by stakeholders
Design & Planning | 16/04/2024 | 30/05/2024 | Product & UX Team | Wireframes, process flow diagrams | Pending | Design review meeting
Development & Testing | 01/06/2024 | 31/08/2024 | Engineering & QA Team | Functional software, test cases, bug reports | Scheduled | Alpha version release
Deployment & Go-Live | 01/09/2024 | 15/09/2024 | Operations & IT Team | Live system rollout, user training materials | Planned | User acceptance testing completed
Post-Launch Review & Optimization | 16/09/2024 | 30/10/2024 | Operations & Feedback Team | Performance reports, improvement plan | Scheduled | Quarterly review meeting