## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Notes
Project Initiation Meeting | 2024-03-15 | 2024-03-15 | Operations Manager | In Progress | Finalize project scope and objectives.
Resource Allocation Plan | 2024-03-18 | 2024-03-22 | HR Director | Pending | Determine team assignments and availability.
Process Workflow Design | 2024-03-25 | 2024-04-05 | Operations Lead | Not Started | Create detailed operational workflows.
System Integration Review | 2024-04-10 | 2024-04-15 | IT Coordinator | Scheduled | Validate integration with existing platforms.
Project Kickoff Workshop | 2024-04-20 | 2024-04-20 | Project Manager | Planned | All stakeholders will participate.