## Worksheet
Task | Start Date | End Date | Responsible | Status | Progress (%) | Milestones
Project Initiation | 2024-01-15 | 2024-01-31 | Jane Doe | Completed | 100% | Kick-off Meeting, Scope Finalization
Market Research | 2024-02-01 | 2024-02-15 | John Smith | In Progress | 60% | Data Collection Complete, Report Drafted
Product Design | 2024-02-16 | 2024-03-31 | Lisa Wong | Not Started | 0% | Concept Review, Prototyping Phase
Development Phase | 2024-04-01 | 2024-06-30 | Mike Chen | Not Started | 0% | Alpha Release, Beta Testing Plan
Testing & QA | 2024-07-01 | 2024-07-31 | Sarah Lee | Not Started | 0% | Bug Resolution, User Acceptance Testing
Launch & Deployment | 2024-08-01 | 2024-08-15 | David Kim | Not Started | 0% | Go-Live, Training Sessions, Post-Launch Support