## Worksheet
Project ID | Project Name | Owner | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone | Risk Level
PROJ-2024-001 | Annual Customer Onboarding System Upgrade | Jane Smith | 2024-03-15 | 2024-11-30 | In Progress | 500,000 | 375,420 | 75% | Complete User Training Module by 2024-10-15 | Moderate
PROJ-2024-002 | Supply Chain Optimization Initiative | Michael Chen | 2024-04-10 | 2025-01-31 | Pending Approval | 850,000 | — | — | Finalize Vendor Evaluation by 2024-06-30 | High
PROJ-2024-003 | Annual IT Infrastructure Modernization | Sarah Kim | 2024-05-01 | 2024-12-31 | On Track | 1,200,000 | 987,654 | 82% | Deploy Cloud Services by 2024-11-15 | Low
PROJ-2024-004 | Employee Wellness Program Rollout | David Park | 2024-06-15 | 2024-11-30 | Active | 150,000 | 138,975 | 92% | Pilot Feedback Review by 2024-10-31 | Limited