## Worksheet
Project ID | Project Name | Owner | Start Date | End Date | Status | Budget (USD) | Current Phase | Progress (%) | Next Milestone
PROJ-001 | Market Expansion in EU | Sarah Johnson | 2024-03-15 | 2024-08-30 | On Track | $150,000 | Market Research & Planning | 65% | Complete Regional Analysis by May 31
PROJ-002 | Digital Transformation Initiative | David Chen | 2024-04-01 | 2025-12-31 | In Progress | $750,000 | System Integration Phase | 40% | Deploy CRM Module by June 15
PROJ-003 | Supply Chain Optimization | Lisa Moreno | 2024-05-10 | 2024-11-30 | At Risk | $220,000 | Vendor Assessment | 25% | Identify Backup Suppliers by June 10
PROJ-004 | Customer Service Portal Launch | James Rivera | 2024-06-15 | 2024-09-30 | On Track | $95,000 | Beta Testing Phase | 85% | Public Launch on August 1