## Worksheet
Project ID | Project Name | Owner | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone
PROJ-2024-001 | Customer Onboarding Platform Launch | Sarah Johnson | 2024-03-15 | 2024-06-30 | In Progress | 150,000 | 98,500 | 65% | User Testing Phase
PROJ-2024-002 | Supply Chain Optimization Initiative | James Rivera | 2024-04-01 | 2024-09-30 | Planning | 250,000 | -- | 15% | Vendor Assessment Complete
PROJ-2024-003 | Marketing Automation Upgrade | Lisa Chen | 2024-05-10 | 2024-08-15 | On Track | 75,000 | 62,300 | 83% | Final Review & Deployment
PROJ-2024-004 | Remote Work Policy Enhancement | Michael Torres | 2024-03-30 | 2024-11-15 | Approved | 50,000 | 38,900 | 78% | Training Rollout (Q4)