## Worksheet
Project Name | Owner | Start Date | End Date th> | Status | Weekly Objective | Key Deliverables | Risks & Issues | Next Week Action Items
Product Launch Q4 | Sarah Johnson | 2023-10-01 | 2023-10-31 | On Track | Finalize marketing campaign content | Launch website, social media rollout | Budget overrun risk; delayed supplier delivery | Secure final approvals by Friday
Sales Process Optimization | Michael Chen | 2023-09-15 | 2023-11-15 | In Progress | Implement new CRM workflow | Updated sales dashboard, training materials | User resistance; technical integration delays | Conduct user feedback session next week
Team Onboarding Program | Lisa Patel | 2023-09-25 | 2023-11-30 | Planned | Develop new onboarding curriculum | Onboarding checklist, orientation sessions | Low headcount; limited training budget | Finalize curriculum by end of week