## Worksheet
Task ID | Task Description | Owner | Due Date | Priority Level | Status | Assigned To Department | Estimated Hours | Actual Hours | Progress (%) | Attachments | Notes
OP-TK-001 | Conduct quarterly business review with key stakeholders | Jane Smith | 2024-04-30 | High | In Progress | Business Operations | 8 | 6.5 | 81% | Report_2024_Q1.pdf | Review meeting minutes to be shared with finance team.
OP-TK-002 | Update internal SOPs for procurement process | Michael Chen | 2024-05-15 | Middle | Pending Approval | Operations & Compliance | 12 | 0 | 0% | SOP_Draft_Procurement.docx | Draft requires feedback from legal and finance departments.
OP-TK-003 | Organize cross-functional team for new product launch | Sarah Lee | 2024-06-10 | High | Not Started | Product Development & Ops | 18 | 0 | 0% | Team_Proposal_v2.pptx | Finalize agenda and assign roles by May 31.
OP-TK-004 | Review vendor performance and renew contracts | David Rodriguez | 2024-05-25 | Middle | Planned | Sourcing & Procurement | 10 | 0 | 0% | Vendor_Performance_2024.xlsx | Include KPIs and negotiation targets.