## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Progress (%) | Comments
BO-001 | Conduct monthly business review meeting | John Smith | 2023-10-15 | Medium | In Progress | 60% | Need to include financial performance metrics.
BO-002 | Update vendor contracts and renewals | Sarah Lee | 2023-11-01 | High | Not Started | 0% | Review all active contracts by end of September.
BO-003 | Optimize supply chain logistics | Michael Chen | 2023-12-10 | High | Planned | 0% | Initial market analysis completed; awaiting budget approval.
BO-004 | Prepare Q4 operational budget | Emily Davis | 2023-10-30 | Medium | In Progress | 45% | Finalizing cost projections from department heads.
BO-005 | Conduct employee performance review cycle | David Kim | 2023-11-15 | Medium | Not Started | 0% | Training session scheduled for early October.